## Current Iteration
|  | Iteration Number: |  |  |  | 3
|  | Expected Total effort: |  |  |  | 115
|  | Days In Sprint: |  |  |  | 6
Burndown Chart
User Stories |  | Days (Points Completed) | [5 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | Task Balance | Percentage Completed
SharePoint Installation and configuaration | 4 | 1 | 2 | 2 | 0 | 0 | 0 | -1 | 125%
Develop home page and courses page | 21 | 1 | 8 | 6 | 3 | 3 | 1 | -1 | 104.8%
Develop news, alumni and pages | 34 | 9 | 7 | 7 | 5 | 3 | 4 | -1 | 102.9%
Develop enqury page and data storage system | 32 | 10 | 11 | 8 | 5 | 3 | 4 | -9 | 128.1%
Develop information about school / college page | 8 | 6 | 6 | 3 | 3 | 1 | 0 | -11 | 237.5%
Develop alumni number form and its workflow | 20 | 2 | 9 | 8 | 7 | 6 | 2 | -14 | 170%
Effort Remaining | 115 | 87 | 46 | 14 | -9 | -25 | -36 | -36 | 131.3%
Ideal Trend | 115 | 95.8333 | 76.6667 | 57.5 | 38.3333 | 19.1667 | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days